## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished | Assigned To | Status
1 | Set up Git repo and create project structure | 4 | 5 | 1 | Andy | Complete
2 | Setting up the SQL database and storing non user information | 4 | 4 | 1 | Brodye/Jacob | Complete
3 | Create a Nav bar to route to all the pages | 3 | 5 | 1 | Ethan | Complete
4 | Create a settings page | 4 | 5 | 1 | Marcus | Complete
5 | Create a profile page | 6 | 4 | 1 | Andy | Complete
6 | User registration and sign in (basic version) | 5 | 3 | 1 | Ethan | Complete
7 | Design the home page | 5 | 4 | 1 | Ethan/Marcus | Complete
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22