## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished | Assigned To | Status
1 | Set up Git repo and create project structure | 4 | 5 | 1 | Andy | Complete
2 | Setting up the SQL database and storing non user information | 4 | 4 | 1 | Brodye/Jacob | Complete
3 | Create a Nav bar to route to all the pages | 3 | 5 | 1 | Ethan | Complete
4 | Create a settings page | 4 | 5 | 1 | Marcus | Complete
5 | Create a profile page | 6 | 4 | 1 | Andy | Complete
6 | User registration and sign in (basic version) | 5 | 3 | 1 | Ethan | Complete
7 | Design the home page | 5 | 4 | 1 | Ethan/Marcus | Complete
8 | Deploy to Server | 5 | 5 | 2 | Andy | Complete
9 | Finish Profile Page | 10 | 5 | 2 | Brodye | Complete
10 | Networking Page | 10 | 5 | 2 | Jacob | Complete
11 | Connect Frontend to Backend | 10 | 5 | 2 | Brodye/Ethan | Complete
12 | Complete User Authentication | 8 | 5 | 2 | Ethan | Complete
13 | Complete Favorites Page | 10 | 5 | 2 | Marcus/Ethan | Complete
14 | Set Up CI/CD Pipeline | 15 | 5 | 2 | Andy | Complete
15 | Automate Python Script to check for new clubs each week | 2 | 3 | 2 | Andy | Complete
16
17
18
19
20
21
22